## Data
Item Key | Summary of Initiatives | Status | Active | Current Phase | Start Date | End Date | Duration | Offset Days | Overrun Days | Total Cost | Item Color | Code
SE11-01 | Punchlist Due Dilligence | Done | TRUE | FALSE | 2025-03-18 | 2025-03-19 | 1 | 76 | 1 | 0 | Purple | 0
SE11-02 | Initial Site Survey | Done | TRUE | FALSE | 2025-03-19 | 2025-03-24 | 5 | 77 | 7 | 0 | Dark Blue | 1
SE11-03 | Retain Real Estate Attorney | To Do | TRUE | TRUE | 2025-03-24 | 2025-03-25 | 1 | 82 | 6 | 0 | Light Blue | 2
SE11-04 | Review & Sign Contracts | To Do | TRUE | TRUE | 2025-03-25 | 2025-03-27 | 2 | 83 | 8 | 0 | Light Blue | 2
SE11-05 | Obtain Building Permits | To Do | TRUE | FALSE | 2025-03-27 | 2025-03-28 | 1 | 85 | 20 | 0 | Grey | 3
SE11-06 | Interior Design Review | To Do | TRUE | FALSE | 2025-03-28 | 2025-04-04 | 7 | 86 | 8 | 0 | Light Blue | 2
SE11-07 | Order Appliances & Vanities | To Do | TRUE | FALSE | 2025-04-04 | 2025-04-09 | 5 | 93 | 15 | 0 | Cyan | 5
SE11-08 | Order Cabinetry (Full Home) | To Do | TRUE | FALSE | 2025-04-04 | 2025-04-09 | 5 | 93 | 17 | 0 | Cyan | 5
SE11-09 | Order Hardware & Fixtures | To Do | TRUE | FALSE | 2025-04-04 | 2025-04-09 | 5 | 93 | 16 | 21000 | Cyan | 5
SE11-10 | Order Tile & Backsplash | To Do | TRUE | FALSE | 2025-04-04 | 2025-04-09 | 5 | 93 | 6 | 9045 | Cyan | 5
SE11-11 | On-Site Contruction Begins | To Do | TRUE | FALSE | 2025-04-09 | 2025-04-10 | 1 | 98 | 19 | 0 | Blue | 4
SE11-12 | Equipment / Tool Rental | To Do | TRUE | FALSE | 2025-04-09 | 2025-04-23 | 14 | 98 | 2 | 1750 | Blue | 4
SE11-13 | Initial Site Clearing & Prep | To Do | TRUE | FALSE | 2025-04-09 | 2025-04-11 | 2 | 98 | 11 | 0 | Blue | 4
SE11-14 | Temporary Utility Instillation | To Do | TRUE | FALSE | 2025-04-11 | 2025-04-12 | 1 | 100 | 2 | 2000 | Blue | 4
SE11-15 | Demolition of Structure | To Do | TRUE | FALSE | 2025-04-12 | 2025-04-19 | 7 | 101 | 16 | 34000 | Blue | 4
SE11-16 | Carting (Waste Materials) | To Do | TRUE | FALSE | 2025-04-12 | 2025-04-19 | 7 | 101 | 9 | 9500 | Blue | 4
SE11-17 | Rear Footing & Step Instillation | To Do | TRUE | FALSE | 2025-04-19 | 2025-04-21 | 2 | 108 | 0 | 11400 | Blue | 4
SE11-18 | Pour Foundation Walls & Slab | To Do | TRUE | FALSE | 2025-04-21 | 2025-04-23 | 2 | 110 | 14 | 0 | Blue | 4
SE11-19 | Foundation Inspection #1 | To Do | TRUE | FALSE | 2025-04-23 | 2025-04-24 | 1 | 112 | 0 | 0 | Grey | 3
SE11-20 | Waterproof Concrete Foundation | To Do | TRUE | FALSE | 2025-04-24 | 2025-04-29 | 5 | 113 | 9 | 0 | Blue | 4
SE11-21 | Backfill Concete Foundaiton | To Do | TRUE | FALSE | 2025-04-29 | 2025-05-01 | 2 | 118 | 15 | 0 | Blue | 4
SE11-22 | Full Utility Tie-In (Con Edison) | To Do | TRUE | FALSE | 2025-05-01 | 2025-05-06 | 5 | 120 | 7 | 0 | Blue | 4
SE11-23 | Foundation Inspection #2 | To Do | TRUE | FALSE | 2025-05-06 | 2025-05-07 | 1 | 125 | 10 | 0 | Grey | 3
SE11-24 | Strucural Steel Instillation | To Do | TRUE | FALSE | 2025-05-07 | 2025-05-08 | 1 | 126 | 0 | 19645 | Blue | 4
SE11-25 | Framing (Structure) | To Do | TRUE | FALSE | 2025-05-08 | 2025-05-22 | 14 | 127 | 11 | 56200 | Blue | 4
SE11-26 | Copper Flashing Instillation | To Do | TRUE | FALSE | 2025-05-22 | 2025-05-24 | 2 | 141 | 4 | 7825 | Blue | 4
SE11-27 | Door & Window Instillation | To Do | TRUE | FALSE | 2025-05-24 | 2025-05-31 | 7 | 143 | 5 | 83617 | Blue | 4
SE11-28 | Garage Door Instillation | To Do | TRUE | FALSE | 2025-05-31 | 2025-06-02 | 2 | 150 | 1 | 14000 | Blue | 4
SE11-29 | Framing Inspection | To Do | TRUE | FALSE | 2025-06-02 | 2025-06-03 | 1 | 152 | 16 | 0 | Grey | 3
SE11-30 | Roof Shingle Instillation | To Do | TRUE | FALSE | 2025-06-03 | 2025-06-10 | 7 | 153 | 18 | 2800 | Blue | 4
SE11-31 | Rough Electrial Instillation | To Do | TRUE | FALSE | 2025-06-10 | 2025-06-24 | 14 | 160 | 16 | 91426 | Blue | 4
SE11-32 | Rough Plumbing Instillation | To Do | TRUE | FALSE | 2025-06-24 | 2025-07-08 | 14 | 174 | 8 | 59760 | Blue | 4
SE11-33 | Plumbing & Electrical Inspection | To Do | TRUE | FALSE | 2025-07-08 | 2025-07-09 | 1 | 188 | 12 | 0 | Grey | 3
SE11-34 | HVAC Duct Work Instillation | To Do | TRUE | FALSE | 2025-07-09 | 2025-07-16 | 7 | 189 | 15 | 54740 | Blue | 4
SE11-35 | Exterior Siding & Paint | To Do | TRUE | FALSE | 2025-07-16 | 2025-07-30 | 14 | 196 | 8 | 31500 | Blue | 4
SE11-36 | Exterior Trim Instillation | To Do | TRUE | FALSE | 2025-07-30 | 2025-08-04 | 5 | 210 | 4 | 59765 | Blue | 4
SE11-37 | Composite Shutter Instillation | To Do | TRUE | FALSE | 2025-07-30 | 2025-08-04 | 5 | 210 | 5 | 6258 | Blue | 4
SE11-38 | Insulation Instillation (Frame) | To Do | TRUE | FALSE | 2025-08-04 | 2025-08-11 | 7 | 215 | 16 | 17204 | Blue | 4
SE11-39 | Gutter & Leader Instillation | To Do | TRUE | FALSE | 2025-08-04 | 2025-08-11 | 7 | 215 | 4 | 5880 | Blue | 4
SE11-40 | Vapor Barrier & Flashing | To Do | TRUE | FALSE | 2025-08-11 | 2025-08-13 | 2 | 222 | 0 | 1800 | Blue | 4
SE11-41 | Weatherproofing Inspection | To Do | TRUE | FALSE | 2025-08-13 | 2025-08-18 | 5 | 224 | 18 | 0 | Grey | 3
SE11-42 | Landscaping Design Review | To Do | TRUE | FALSE | 2025-08-18 | 2025-08-25 | 7 | 229 | 16 | 0 | Light Blue | 2
SE11-43 | Order Landscaping & Materials | To Do | TRUE | FALSE | 2025-08-25 | 2025-08-26 | 1 | 236 | 4 | 0 | Cyan | 5
SE11-44 | Medicine Cabinet Framing | To Do | TRUE | FALSE | 2025-08-26 | 2025-08-27 | 1 | 237 | 11 | 0 | Blue | 4
SE11-45 | Drywall Instillation | To Do | TRUE | FALSE | 2025-08-27 | 2025-09-01 | 5 | 238 | 17 | 18250 | Blue | 4
SE11-46 | Recessed Lighting Instillation | To Do | TRUE | FALSE | 2025-09-01 | 2025-09-06 | 5 | 243 | 4 | 0 | Blue | 4
SE11-47 | Hardwood Floor Instillation | To Do | TRUE | FALSE | 2025-09-06 | 2025-09-08 | 2 | 248 | 14 | 26826 | Blue | 4
SE11-48 | Interior Rail Instillation | To Do | TRUE | FALSE | 2025-09-06 | 2025-09-08 | 2 | 248 | 19 | 7840 | Blue | 4
SE11-49 | Interior Trim Instillation | To Do | TRUE | FALSE | 2025-09-06 | 2025-09-11 | 5 | 248 | 13 | 70986 | Blue | 4
SE11-50 | Paint Walls, Trim & Ceilings | To Do | TRUE | FALSE | 2025-09-11 | 2025-09-25 | 14 | 253 | 7 | 31275 | Blue | 4
SE11-51 | Tile & Backsplaash Instillation | To Do | TRUE | FALSE | 2025-09-25 | 2025-09-30 | 5 | 267 | 9 | 21590 | Blue | 4
SE11-52 | Appliance & Vanity Instillation | To Do | TRUE | FALSE | 2025-09-25 | 2025-09-30 | 5 | 267 | 17 | 5900 | Blue | 4
SE11-53 | Cabinetry & Countertop Instillation | To Do | TRUE | FALSE | 2025-09-25 | 2025-09-30 | 5 | 267 | 20 | 0 | Blue | 4
SE11-54 | Mirror & Accessory Instillation | To Do | TRUE | FALSE | 2025-09-30 | 2025-10-01 | 1 | 272 | 7 | 2600 | Blue | 4
SE11-55 | Fixture & Hardware Instillation | To Do | TRUE | FALSE | 2025-10-01 | 2025-10-03 | 2 | 273 | 17 | 3500 | Blue | 4
SE11-56 | Alarm System Instillation | To Do | TRUE | FALSE | 2025-10-01 | 2025-10-03 | 2 | 273 | 15 | 0 | Blue | 4
SE11-57 | Floor Stain (1st Coat) | To Do | TRUE | FALSE | 2025-10-03 | 2025-10-05 | 2 | 275 | 4 | 0 | Blue | 4
SE11-58 | Floor Stain (2nd Coat) | To Do | TRUE | FALSE | 2025-10-05 | 2025-10-10 | 5 | 277 | 6 | 0 | Blue | 4
SE11-59 | Final Grading & Landscaping | To Do | TRUE | FALSE | 2025-10-05 | 2025-10-12 | 7 | 277 | 3 | 0 | Blue | 4
SE11-60 | Irrigation Instillation | To Do | TRUE | FALSE | 2025-10-05 | 2025-10-12 | 7 | 277 | 1 | 0 | Blue | 4
SE11-61 | Blue Stone Patio Instillation | To Do | TRUE | FALSE | 2025-10-12 | 2025-10-14 | 2 | 284 | 14 | 18900 | Blue | 4
SE11-62 | Perimeter Fencing Instillation | To Do | TRUE | FALSE | 2025-10-14 | 2025-10-19 | 5 | 286 | 6 | 0 | Blue | 4
SE11-63 | Final Site Cleanup | To Do | TRUE | FALSE | 2025-10-19 | 2025-10-21 | 2 | 291 | 0 | 3000 | Blue | 4
SE11-64 | Site Survey (Pre C of O) | To Do | TRUE | FALSE | 2025-10-21 | 2025-10-22 | 1 | 293 | 17 | 0 | Dark Blue | 1
SE11-65 | Deck & Patio Inspection | To Do | TRUE | FALSE | 2025-10-22 | 2025-10-23 | 1 | 294 | 10 | 0 | Grey | 3
SE11-66 | Final Inspection (C of O) | To Do | TRUE | FALSE | 2025-10-23 | 2025-10-24 | 1 | 295 | 7 | 0 | Grey | 3
SE11-67 | Moving Services (Post Close) | To Do | TRUE | FALSE | 2025-10-24 | 2025-10-25 | 1 | 296 | 2 | 0 | Blue | 4
SE11-68 | Final Contractor Payment Due | To Do | TRUE | FALSE | 2025-10-25 | 2025-10-26 | 1 | 297 | 0 | 0 | Blue | 4
Formulas:
End Date = [Start Date]+[Duration]
Start Date = [End Date, row above]
Start Date = [Start Date, row above]

## Pricing Info
`
11 Clinton Lane - Unit / Material Cost
Current Date: | 2025-03-24 |  |  |  | Expected Completion Date |  | 2025-10-26
Project Start: | 2025-01-01 |  |  |  | Total Project Timeline (Hrs) |  | 2376
Lot Size | 43560 |  |  |  | Construction Cost |  | 690014.7 |  |  | Builder Grade (%) | 75%
Building SF | 4000 |  |  |  | GC Fee (%) | 15% | 121767.3 |  |  | Market Grade (%) | 85%
# of Stories | 2 |  |  |  | Punchlist Fee (%) | 5% | 34500.735 |  |  | Punchlist Grade (%) | 100%
Above Grade SF | 3400 |  |  |  | Total Project Cost |  | 846282.735 |  |  | Design Grade (%) | 115%
Below Grade SF | 600 |  |  |  | $ per SF Cost |  | 211.5707 |  |  | Luxuary Grade (%) | 125%
Unit / Service Desciption | Unit Cost (1) | % Market Grade | Unit Cost + Grade | Total Units / SF | Labor Rate (Hr) | Expected Hours | Instillation Cost | Total Unit Cost | Waste (0.00%) | Final Unit Cost | Initiative Key | Initiative Name
Survey / Staking (By Owner) | 0 | 100% | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-02 | Initial Site Survey
Portable Restroom | 2000 | 100% | 2000 | 1 | 2000 | 0 | 0 | 2000 | 0 | 2000 | SE11-14 | Temporary Utility Instillation
Demolition | 34000 | 100% | 34000 | 1 | 34000 | 0 | 0 | 34000 | 0 | 34000 | SE11-15 | Demolition of Structure
Carting (Allowance) | 9500 | 100% | 9500 | 1 | 9500 | 0 | 0 | 9500 | 0 | 9500 | SE11-16 | Carting (Waste Materials)
Rear Foot / Steps | 11400 | 100% | 11400 | 1 | 11400 | 0 | 0 | 11400 | 0 | 11400 | SE11-17 | Rear Footing & Step Instillation
Structural Steel | 19645 | 100% | 19645 | 1 | 19645 | 0 | 0 | 19645 | 0 | 19645 | SE11-24 | Strucural Steel Instillation
Bluestone Patio Rear (No Border) | 18900 | 100% | 18900 | 1 | 18900 | 0 | 0 | 18900 | 0 | 18900 | SE11-61 | Blue Stone Patio Instillation
Interior Rails (Red Oak) | 7840 | 100% | 7840 | 1 | 7840 | 0 | 0 | 7840 | 0 | 7840 | SE11-48 | Interior Rail Instillation
Framing (Interior & Exterior) | 56200 | 100% | 56200 | 1 | 56200 | 0 | 0 | 56200 | 0 | 56200 | SE11-25 | Framing (Structure)
Electrical / Generator (22kw) | 91426 | 100% | 91426 | 1 | 91426 | 0 | 0 | 91426 | 0 | 91426 | SE11-31 | Rough Electrial Instillation
Insulation (No Attic) | 17204 | 100% | 17204 | 1 | 17204 | 0 | 0 | 17204 | 0 | 17204 | SE11-38 | Insulation Instillation (Frame)
HVAC (2 Hydro Systems / 3 Zones) | 54740 | 100% | 54740 | 1 | 54740 | 0 | 0 | 54740 | 0 | 54740 | SE11-34 | HVAC Duct Work Instillation
Plumbing / Heating / Gas Work | 59760 | 100% | 59760 | 1 | 59760 | 0 | 0 | 59760 | 0 | 59760 | SE11-32 | Rough Plumbing Instillation
Plumbing Fixture Allowance | 21000 | 100% | 21000 | 1 | 21000 | 0 | 0 | 21000 | 0 | 21000 | SE11-09 | Order Hardware & Fixtures
Drywall (Per Plan) | 18250 | 100% | 18250 | 1 | 18250 | 0 | 0 | 18250 | 0 | 18250 | SE11-45 | Drywall Instillation
Roofing (Patch to Match) | 2800 | 100% | 2800 | 1 | 2800 | 0 | 0 | 2800 | 0 | 2800 | SE11-30 | Roof Shingle Instillation
Copper Roofs / Flashing | 7825 | 100% | 7825 | 1 | 7825 | 0 | 0 | 7825 | 0 | 7825 | SE11-26 | Copper Flashing Instillation
Exterior Doors / Windows | 83617 | 100% | 83617 | 1 | 83617 | 0 | 0 | 83617 | 0 | 83617 | SE11-27 | Door & Window Instillation
Composite Shutters (7 Pair) | 6258 | 100% | 6258 | 1 | 6258 | 0 | 0 | 6258 | 0 | 6258 | SE11-37 | Composite Shutter Instillation
Exterior Trim | 44465 | 100% | 44465 | 1 | 44465 | 0 | 0 | 44465 | 0 | 44465 | SE11-36 | Exterior Trim Instillation
Garage Doors (3x?) | 14000 | 100% | 14000 | 1 | 14000 | 0 | 0 | 14000 | 0 | 14000 | SE11-28 | Garage Door Instillation
Gutters / Leaders (6K White) | 5880 | 100% | 5880 | 1 | 5880 | 0 | 0 | 5880 | 0 | 5880 | SE11-39 | Gutter & Leader Instillation
Vapor Barrier / Window / Door Flashing | 1800 | 100% | 1800 | 1 | 1800 | 0 | 0 | 1800 | 0 | 1800 | SE11-40 | Vapor Barrier & Flashing
Exterior Siding / Hardi Plank 6" | 31500 | 100% | 31500 | 1 | 31500 | 0 | 0 | 31500 | 0 | 31500 | SE11-35 | Exterior Siding & Paint
Exterior Paint (Trim Only) | 15300 | 100% | 15300 | 1 | 15300 | 0 | 0 | 15300 | 0 | 15300 | SE11-36 | Exterior Trim Instillation
Tile Allowance | 9045 | 100% | 9045 | 1 | 9045 | 0 | 0 | 9045 | 0 | 9045 | SE11-10 | Order Tile & Backsplash
Tile Labor | 21590 | 100% | 21590 | 1 | 21590 | 0 | 0 | 21590 | 0 | 21590 | SE11-51 | Tile & Backsplaash Instillation
Hardwood Floors (3 1/4 Red Oak) | 26826 | 100% | 26826 | 1 | 26826 | 0 | 0 | 26826 | 0 | 26826 | SE11-47 | Hardwood Floor Instillation
Interior Trim | 70986 | 100% | 70986 | 1 | 70986 | 0 | 0 | 70986 | 0 | 70986 | SE11-49 | Interior Trim Instillation
Interior Paint / Primer | 31275 | 100% | 31275 | 1 | 31275 | 0 | 0 | 31275 | 0 | 31275 | SE11-50 | Paint Walls, Trim & Ceilings
Vanity Instillation | 2700 | 100% | 2700 | 1 | 2700 | 0 | 0 | 2700 | 0 | 2700 | SE11-52 | Appliance & Vanity Instillation
Shower Doors / Paritions (Primary) | 3500 | 100% | 3500 | 1 | 3500 | 0 | 0 | 3500 | 0 | 3500 | SE11-55 | Fixture & Hardware Instillation
Appliance Instillaton | 3200 | 100% | 3200 | 1 | 3200 | 0 | 0 | 3200 | 0 | 3200 | SE11-52 | Appliance & Vanity Instillation
Mirror / Accessory Installation | 2600 | 100% | 2600 | 1 | 2600 | 0 | 0 | 2600 | 0 | 2600 | SE11-54 | Mirror & Accessory Instillation
Site Clean up (Final) | 3000 | 100% | 3000 | 1 | 3000 | 0 | 0 | 3000 | 0 | 3000 | SE11-63 | Final Site Cleanup
Equipment / Tool Rental | 1000 | 100% | 1000 | 1 | 1000 | 0 | 0 | 1000 | 0 | 1000 | SE11-12 | Equipment / Tool Rental
Misc. Job Supplies | 750 | 100% | 750 | 1 | 750 | 0 | 0 | 750 | 0 | 750 | SE11-12 | Equipment / Tool Rental
[9 empty] | 0 | 811782
Items Not Included: | Unit Cost (1) | % Market Grade | Unit Cost + Grade | Total Units / SF | Labor Rate (Hr) | Expected Hours | Instillation Cost | Total Unit Cost | Waste (10.00%) | Final Unit Cost | Initiative Key | Initiative Name
Peremiter Fencing | 0 | 100% | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-62 | Perimeter Fencing Instillation
Kitchen Appliances | 0 | 100% | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-07 | Order Appliances & Vanities
Kitchen & Bathroom Cabinetry | 0 | 100% | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-08 | Order Cabinetry (Full Home)
Bathroom Vanities | 0 | 100% | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-07 | Order Appliances & Vanities
Lighiting Fixtures & Hardware | 0 | 100% | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-09 | Order Hardware & Fixtures
Tile & Backspalsh | 0 | 100% | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-10 | Order Tile & Backsplash
Final Grading / Landscaping | 0 | 100% | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-59 | Final Grading & Landscaping
Irrigation System (By Owner) | 0 | 100% | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-60 | Irrigation Instillation
Property Fencing | 0 | 100% | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-62 | Perimeter Fencing Instillation
Hourly Services (Designer) | 0 | 100% | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-68 | Final Contractor Payment Due
Hourly Services (Punchlist) | 0 | 100% | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-68 | Final Contractor Payment Due
Initial Site Survey | 0 | 100% | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-64
Final Site Survey | 0 | 100% | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-64 | Site Survey (Pre C of O)
C of O Inspection | 0 | 100% | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-66 | Final Inspection (C of O)
Alarm System (By Owner) | 0 | 100% | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-56
Building Permit Fees | 0 | 100% | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | SE11-05 | Obtain Building Permits
[9 empty] | 0 | 0

## Color Code
Code | Color
0 | Purple
1 | Dark Blue
2 | Light Blue
3 | Grey
4 | Blue
5 | Cyan