## Data
KEY | Inniative Cost & Description | Accepted Cost | Market Cost | Realized Cost | $ Difference | % Difference | Item Status | Item Active | Current Phase | Start Date | End Date | Duration | offset | Item Color | Color Code | Notes
1 | Initial Site Survey (By Owner) | 0 | 0 | 0 | 0 | #DIV/0! | Done | TRUE | FALSE | 2025-01-01 | 2025-01-02 | 1 | 0 | Dark Blue | 1 | No notes
2 | Archtectual Plans (By Owner) | 0 | 0 | 0 | 0 | #DIV/0! | Done | TRUE | FALSE | 2025-01-02 | 2025-02-01 | 30 | 1 | Dark Blue | 1 | This is a longer bigger note just to test longer and bigger notes.
3 | Architectual / Planning / Zonning | 0 | 0 | 0 | 0 | #DIV/0! | Done | TRUE | FALSE | 2025-02-01 | 2025-02-16 | 15 | 31 | Grey | 3
4 | Constructuction Plans (By Owner) | 0 | 0 | 0 | 0 | #DIV/0! | Done | TRUE | FALSE | 2025-02-16 | 2025-02-23 | 7 | 46 | Light Blue | 2 | No notes
5 | Proposal & Design Review | 0 | 0 | 0 | 0 | #DIV/0! | Done | TRUE | FALSE | 2025-02-23 | 2025-03-10 | 15 | 53 | Light Blue | 2 | No notes
6 | Sign Contracts & Begin Ordering | 0 | 0 | 0 | 0 | #DIV/0! | Done | TRUE | FALSE | 2025-03-10 | 2025-04-09 | 30 | 68 | Light Blue | 2 | No notes
7 | Building Permit (By Owner) | 0 | 0 | 0 | 0 | #DIV/0! | To Do | TRUE | TRUE | 2025-04-09 | 2025-04-10 | 1 | 98 | Cyan | 5 | No notes
8 | Kitchen & Cabinets (By Owner) | 0 | 0 | 0 | 0 | #DIV/0! | To Do | TRUE | TRUE | 2025-04-09 | 2025-04-30 | 21 | 98 | Cyan | 5 | No notes
9 | Countertops (By Owner) | 0 | 0 | 0 | 0 | #DIV/0! | To Do | TRUE | TRUE | 2025-04-09 | 2025-04-30 | 21 | 98 | Cyan | 5 | No notes
10 | Bathroom Vanities (By Owner) | 0 | 0 | 0 | 0 | #DIV/0! | To Do | TRUE | TRUE | 2025-04-09 | 2025-04-30 | 21 | 98 | Cyan | 5 | No notes
11 | Appliances (By Owner) | 0 | 0 | 0 | 0 | #DIV/0! | To Do | TRUE | TRUE | 2025-04-09 | 2025-04-30 | 21 | 98 | Cyan | 5 | No notes
12 | Tile (By Owner) | 9045 | 9045 | 0 | -9045 | -100% | To Do | TRUE | TRUE | 2025-04-09 | 2025-04-30 | 21 | 98 | Cyan | 5 | No notes
13 | Alarm System (By Owner) | 0 | 0 | 0 | 0 | #DIV/0! | To Do | TRUE | TRUE | 2025-04-09 | 2025-04-30 | 21 | 98 | Cyan | 5 | No notes
14 | Interior Fixtures (By Owner) | 21000 | 21000 | 0 | -21000 | -100% | To Do | TRUE | TRUE | 2025-04-09 | 2025-04-30 | 21 | 98 | Cyan | 5 | No notes
15 | Temporary Utilities | 2000 | 1800 | 0 | -2000 | -100% | To Do | TRUE | FALSE | 2025-05-01 | 2025-05-03 | 2 | 120 | Blue | 4 | No notes
16 | Demolition (Site & Structure) | 42450 | 28750 | 0 | -42450 | -100% | To Do | TRUE | FALSE | 2025-05-03 | 2025-05-17 | 14 | 122 | Blue | 4 | No notes
17 | Carting & Junking (Allowance) | 10500 | 30000 | 0 | -10500 | -100% | To Do | TRUE | FALSE | 2025-05-03 | 2025-05-17 | 14 | 122 | Blue | 4 | No notes
18 | Inital Site Grading | 0 | 0 | 0 | 0 | #DIV/0! | To Do | TRUE | FALSE | 2025-05-17 | 2025-05-19 | 2 | 136 | Blue | 4 | No notes
19 | Concrete Foundation & Footings | 11400 | 1098 | 0 | -11400 | -100% | To Do | TRUE | FALSE | 2025-05-19 | 2025-05-24 | 5 | 138 | Blue | 4 | No notes
20 | Structural Steel | 19645 | 8500 | 0 | -19645 | -100% | To Do | TRUE | FALSE | 2025-05-19 | 2025-05-24 | 5 | 138 | Blue | 4 | No notes
21 | Inspection (Foundaiton) | 0 | 0 | 0 | 0 | #DIV/0! | To Do | TRUE | FALSE | 2025-05-24 | 2025-05-25 | 1 | 143 | Grey | 3 | No notes
22 | Patio & Deck (Blue Stone) | 18900 | 17714 | 0 | -18900 | -100% | To Do | TRUE | FALSE | 2025-05-25 | 2025-05-30 | 5 | 144 | Blue | 4 | No notes
23 | Inspection (Patio & Deck) | 0 | 0 | 0 | 0 | #DIV/0! | To Do | TRUE | FALSE | 2025-05-30 | 2025-05-31 | 1 | 149 | Grey | 3 | No notes
24 | lnterior Rails & Stairs (Red Oak) | 7840 | 25895 | 0 | -7840 | -100% | To Do | TRUE | FALSE | 2025-05-31 | 2025-06-02 | 2 | 150 | Blue | 4 | No notes
25 | Framing (Interior & Exterior) | 56200 | 34000 | 0 | -56200 | -100% | To Do | TRUE | FALSE | 2025-05-31 | 2025-06-14 | 14 | 150 | Blue | 4 | No notes
26 | Inspection (Framing) | 0 | 0 | 0 | 0 | #DIV/0! | To Do | TRUE | FALSE | 2025-06-14 | 2025-06-15 | 1 | 164 | Grey | 3 | No notes
27 | Rough Electrical & Generator | 128308 | 77600 | 0 | -128308 | -100% | To Do | TRUE | FALSE | 2025-06-15 | 2025-07-06 | 21 | 165 | Blue | 4 | No notes
28 | HVAC (2 Hydro Systems - 3 Zones) | 54740 | 47000 | 0 | -54740 | -100% | To Do | TRUE | FALSE | 2025-06-21 | 2025-07-05 | 14 | 171 | Blue | 4 | No notes
29 | Plumbing / Duct / Gas Work | 71400 | 41000 | 0 | -71400 | -100% | To Do | TRUE | FALSE | 2025-06-21 | 2025-07-05 | 14 | 171 | Blue | 4 | No notes
30 | Insulation (Spray Foam) | 31640 | 17400 | 0 | -31640 | -100% | To Do | TRUE | FALSE | 2025-07-05 | 2025-07-07 | 2 | 185 | Blue | 4 | No notes
31 | Inspection (Plumbing & Electrical) | 0 | 0 | 0 | 0 | #DIV/0! | To Do | TRUE | FALSE | 2025-07-07 | 2025-07-08 | 1 | 187 | Grey | 3 | No notes
32 | Inspection (HVAC) | 0 | 0 | 0 | 0 | #DIV/0! | To Do | TRUE | FALSE | 2025-07-08 | 2025-07-09 | 1 | 188 | Grey | 3 | No notes
33 | Drywall & Wall Patching | 26250 | 23000 | 0 | -26250 | -100% | To Do | TRUE | FALSE | 2025-07-09 | 2025-07-14 | 5 | 189 | Blue | 4 | No notes
34 | Roofing (Patch To Match) | 2800 | 3000 | 0 | -2800 | -100% | To Do | TRUE | FALSE | 2025-07-14 | 2025-07-16 | 2 | 194 | Blue | 4 | No notes
35 | Copper Roofing & Flashing | 7825 | 11000 | 0 | -7825 | -100% | To Do | TRUE | FALSE | 2025-07-16 | 2025-07-18 | 2 | 196 | Blue | 4 | No notes
36 | Exterior Doors & Windows | 83617 | 60561 | 0 | -83617 | -100% | To Do | TRUE | FALSE | 2025-07-18 | 2025-07-25 | 7 | 198 | Blue | 4 | No notes
37 | Composite Shutters (7 Pair) | 6258 | 0 | 0 | -6258 | -100% | To Do | TRUE | FALSE | 2025-07-25 | 2025-07-26 | 1 | 205 | Blue | 4 | No notes
38 | Exterior Trim & Labor | 44465 | 38000 | 0 | -44465 | -100% | To Do | TRUE | FALSE | 2025-07-26 | 2025-08-09 | 14 | 206 | Blue | 4 | No notes
39 | Garage Doors & Motors (2x) | 14000 | 6000 | 0 | -14000 | -100% | To Do | TRUE | FALSE | 2025-08-09 | 2025-08-11 | 2 | 220 | Blue | 4 | No notes
40 | Gutters & Leaders | 5880 | 4800 | 0 | -5880 | -100% | To Do | TRUE | FALSE | 2025-08-09 | 2025-08-11 | 2 | 220 | Blue | 4 | No notes
41 | Door & Window Vapor Barrier | 1800 | 0 | 0 | -1800 | -100% | To Do | TRUE | FALSE | 2025-08-09 | 2025-08-14 | 5 | 220 | Blue | 4 | No notes
42 | Inspection (Weatherproofing) | 0 | 0 | 0 | 0 | #DIV/0! | To Do | TRUE | FALSE | 2025-08-14 | 2025-08-15 | 1 | 225 | Grey | 3 | No notes
43 | Exterior Siding (Hardi Plank 6") | 31500 | 20000 | 0 | -31500 | -100% | To Do | TRUE | FALSE | 2025-08-15 | 2025-08-22 | 7 | 226 | Blue | 4 | No notes
44 | Exterior Paint & Labor | 15300 | 0 | 0 | -15300 | -100% | To Do | TRUE | FALSE | 2025-08-22 | 2025-08-27 | 5 | 233 | Blue | 4 | No notes
45 | TIie Labor | 21590 | 33985 | 0 | -21590 | -100% | To Do | TRUE | FALSE | 2025-08-22 | 2025-09-05 | 14 | 233 | Blue | 4 | No notes
46 | Hardwood Floors (3 1/4" Red Oak) | 26826 | 25345 | 0 | -26826 | -100% | To Do | TRUE | FALSE | 2025-08-22 | 2025-09-05 | 14 | 233 | Blue | 4 | No notes
47 | Interior Trim & Labor | 70986 | 75000 | 0 | -70986 | -100% | To Do | TRUE | FALSE | 2025-08-22 | 2025-09-05 | 14 | 233 | Blue | 4 | No notes
48 | Interior Paint / Stain | 31275 | 25000 | 0 | -31275 | -100% | To Do | TRUE | FALSE | 2025-09-05 | 2025-09-12 | 7 | 247 | Blue | 4 | No notes
49 | Vanity Installation | 2700 | 0 | 0 | -2700 | -100% | To Do | TRUE | FALSE | 2025-09-12 | 2025-09-13 | 1 | 254 | Blue | 4 | No notes
50 | Shower Door Instillation (3 Baths) | 8250 | 0 | 0 | -8250 | -100% | To Do | TRUE | FALSE | 2025-09-12 | 2025-09-13 | 1 | 254 | Blue | 4 | No notes
51 | Appliance Installation | 3200 | 1500 | 0 | -3200 | -100% | To Do | TRUE | FALSE | 2025-09-12 | 2025-09-13 | 1 | 254 | Blue | 4 | No notes
52 | Mirror & Accessory Installation | 2600 | 3500 | 0 | -2600 | -100% | To Do | TRUE | FALSE | 2025-09-12 | 2025-09-13 | 1 | 254 | Blue | 4 | No notes
53 | Grading & Landscaping (By Owner) | 0 | 0 | 0 | 0 | #DIV/0! | To Do | TRUE | FALSE | 2025-09-12 | 2025-09-19 | 7 | 254 | Cyan | 5 | No notes
54 | Irrigation System (Allowance) | 0 | 500 | 0 | 0 | #DIV/0! | To Do | TRUE | FALSE | 2025-09-19 | 2025-09-21 | 2 | 261 | Blue | 4 | No notes
55 | Electric / Radiant Floor Heat | 5900 | 3650 | 0 | -5900 | -100% | To Do | TRUE | FALSE | 2025-09-19 | 2025-09-24 | 5 | 261 | Blue | 4 | No notes
56 | Windows (Attic & Basment) | 7600 | 0 | 0 | -7600 | -100% | To Do | TRUE | FALSE | 2025-09-19 | 2025-09-24 | 5 | 261 | Blue | 4 | No notes
57 | Interior Doors & Hardware | 0 | 17000 | 0 | 0 | #DIV/0! | To Do | TRUE | FALSE | 2025-09-19 | 2025-09-26 | 7 | 261 | Blue | 4 | No notes
58 | Skylights & Fireplace | 0 | 3000 | 0 | 0 | #DIV/0! | To Do | TRUE | FALSE | 2025-09-26 | 2025-09-28 | 2 | 268 | Blue | 4 | No notes
59 | Driveway Demo, Prep & Pavement | 0 | 24800 | 0 | 0 | #DIV/0! | To Do | TRUE | FALSE | 2025-09-28 | 2025-10-12 | 14 | 270 | Blue | 4 | No notes
60 | Replace Entry Columns & Portico | 0 | 6000 | 0 | 0 | #DIV/0! | To Do | TRUE | FALSE | 2025-09-28 | 2025-10-12 | 14 | 270 | Blue | 4 | No notes
61 | Final Site Clean Up | 3000 | 3000 | 0 | -3000 | -100% | To Do | TRUE | FALSE | 2025-10-12 | 2025-10-14 | 2 | 284 | Blue | 4 | No notes
62 | Final Site Survey (By Owner) | 0 | 0 | 0 | 0 | #DIV/0! | To Do | TRUE | FALSE | 2025-10-14 | 2025-10-15 | 1 | 286 | Light Blue | 2 | No notes
63 | Inspection (Final C of O) | 0 | 0 | 0 | 0 | #DIV/0! | To Do | TRUE | FALSE | 2025-10-15 | 2025-10-16 | 1 | 287 | Grey | 3 | No notes
64 | Final Move-In & Furniture | 0 | 0 | 0 | 0 | #DIV/0! | To Do | TRUE | FALSE | 2025-10-16 | 2025-10-17 | 1 | 288 | Cyan | 5 | No notes
65 | Project Supervision | 0 | 20000 | 0 | 0 | #DIV/0! | To Do | FALSE | FALSE | 2025-10-17 | 2025-10-17 | 1 | 289 | Dark Blue | 1 | No notes
66 | Builders Insurance | 0 | 23106 | 0 | 0 | #DIV/0! | To Do | FALSE | FALSE | 2025-10-17 | 2025-10-17 | 1 | 289 | Dark Blue | 1 | No notes
67 | Equipment & Tool Rental | 1000 | 500 | 0 | -1000 | -100% | To Do | FALSE | FALSE | 2025-10-17 | 2025-10-17 | 1 | 289 | Dark Blue | 1 | No notes
68 | Misc. Labor & Supplies | 750 | 0 | 0 | -750 | -100% | To Do | FALSE | FALSE | 2025-10-17 | 2025-10-17 | 1 | 289 | Blue | 4 | No notes
69 | Project Overhead & Profit | 0 | 118995 | 0 | 0 | #DIV/0! | To Do | FALSE | FALSE | 2025-10-17 | 2025-10-17 | 1 | 289 | Dark Blue | 1 | No notes
70 | Interior Design Fees | 0 | 0 | 0 | 0 | #DIV/0! | To Do | FALSE | FALSE | 2025-10-17 | 2025-10-17 | 1 | 289 | Dark Blue | 1 | No notes
71 | Material Waste (10%) | 0 | 0 | 0 | 0 | #DIV/0! | To Do | FALSE | FALSE | 2025-10-17 | 2025-10-17 | 1 | 289 | Blue | 4 | No notes
72 | Contingency Fees (25%) | 0 | 0 | 0 | 0 | #DIV/0! | To Do | FALSE | FALSE | 2025-10-17 | 2025-10-17 | 1 | 289 | Blue | 4 | No notes
73 | Legal / Professional Fees | 0 | 0 | 0 | 0 | #DIV/0! | To Do | FALSE | FALSE | 2025-10-17 | 2025-10-17 | 1 | 289 | Dark Blue | 1 | No notes
74 | Loans & Interest (By Owner) | 0 | 0 | 0 | 0 | #DIV/0! | To Do | FALSE | FALSE | 2025-10-17 | 2025-10-17 | 1 | 289 | Light Blue | 2 | No notes
75 | Punchlist Coordination (1%) | 0 | 0 | 0 | 0 | #DIV/0! | To Do | FALSE | FALSE | 2025-10-17 | 2025-10-17 | 1 | 289 | Purple | 0 | No notes
Formulas:
End Date = [Start Date]+[Duration]
Start Date = [End Date, row above]
Start Date = [Start Date, row above]

## Color Code
Code | Color | Description
0 | Purple | Punchlist Activities
1 | Dark Blue | Professional Reviews
2 | Light Blue | Client Due Dilligence
3 | Grey | Municipal Reviews
4 | Blue | Contrsturction
5 | Cyan | Purchase Orders

## Information
Client Name: | AMDS Consulting Inc.
Contractor: | Chris Fitzgerald Inc.
Address: | 11 Clinton Lane, Harrison, NY 10528
Building SF | 4,000-5,000 SF
Lot Size (SF) | ~ 1.0 Acres
Accept Bid ($) | #REF!
Market Bid ($) | #REF!
Total Cost ($) | #REF!